PolicyOS · Tara

Product Roadmap

Selling-first: a modern, sellable build in July; the connectors + company-brain layer from August — targeting 9–10 connectors/month (MCP-first long tail) on the new 2-devs + 1-QA assumption. Companion to the Gantt workbook (PolicyOS_Tara_Roadmap.xlsx).

Tartan HQ · Internal · v2, 24 Jun 2026 · aggressive timeline on the 2-devs + 1-QA assumption · grounded in the Jun 23 PolicyOS-revamp meeting

Milestones

| Date | Milestone |
| --- | --- |
| Mon 29 Jun 2026 | All PRDs locked (Regulatory with Anmol; UI prototype-link frozen to Devesh; colour scheme confirmed) + AI-system demo. |
| end-July 2026 | Permission layer defined and verified (Sync team + the new dedicated QA) — hard exit-criterion that unlocks Phase B, even though it isn’t a sellable feature. |
| Thu 31 Jul 2026 | Sellable build ready — Regulatory gaps + test-based simulation + UI revamp + AI bot + product tour. |
| Aug → Nov 2026 | Connectors at 9–10 / month once the framework lands — HRMS/proprietary hand-built, long tail MCP-first (two devs + dedicated QA); ~20 connectors by end-September, ~35 by end-November; read-only company brain takes shape. |
| Nov–Dec 2026 | Read-only central brain to GA + context/memory layer + hardening. |
| Q1–Q2 2027 | Agents — pull (Q1), then governed push (Q2). |

Phase A — July 2026: the sellable build

Five deliverables, all PRD-gated (freeze the spec from the prototype link + existing logic before build), prioritised by selling impact — the product is today mostly used to sell. Same BFSI story, sharper product. With two devs the July tracks run in parallel rather than at-risk, and the dedicated QA runs regression continuously from week one.

1. Regulatory gaps   [flagship · sellable]

Goal — the latest, most-asked customer feature — turn an incoming circular into reviewed, approved policy changes.

In scope (July) — the manual path end-to-end: upload a circular → compare against existing policies → AI redline/suggestions → review per item → change request → existing approval workflow; tie in the simulation to show impact.

Out of scope (later) — full auto-scrape of regulator sites — the multi-authority blocker (RBI / SEBI / MCA / MSME) makes it a v1.1; ship manual first.

Pre-work — map the regulator ecosystem (which authorities, where they list, how much is auto-scrapable) before build, with Anmol’s client context.

2. Test-based simulation   [sellable]

Goal — show the impact of a rule change on a test user base (e.g. CIBIL 720→730 ⇒ eligible 70%→60%).

In scope (July) — category-level common metrics (approval rate), client uploads their own test/dummy data; per-policy JSON summary → impact; surfaced in the simulator and in compare-policies, with an AI ask layer.

Out of scope — fully custom per-policy variables — too complex for the month; keep to common schemes. Build it cleanly, separate from the half-baked old test bed.

3. AI bot — unified Tara assistant   [core]

Goal — one RBAC-aware ask surface (replacing the 4+ duplicated AI surfaces).

In scope (July) — generic ask across the policies a user can access (on Home/Dashboard) + per-policy Q&A, with source chips + page citations. Mostly exists in the prototype — productionise it; cut latency; stop dummy-data leakage.

4. UI revamp   [sellable]

Goal — a modern UI — the current grey/black reads dated and the number font is poor.

In scope (July) — confirm the colour scheme, then apply the design system (Devesh). Page order: Login (PLG quick win) → Home/Dashboard → Policy detail + full-screen PDF view → Regulatory / Simulation / PolyGPT → remaining.

Out of scope — custom / 3D per-client dashboards — ship one good generic dashboard.

5. Product guided tour   [polish]

Goal — help first-time users learn the surface.

In scope (July) — a drop-in overlay + tooltips for the first N logins. Small effort, late in the month.

July week-by-week

| Week | Focus |
| --- | --- |
| W1 · Jun 23–29 | PRDs (all 5) · regulator-ecosystem research · colour scheme confirmed · Login design. → Jun 29: PRDs locked + AI demo. |
| W2 · Jun 30–Jul 6 | Regulatory build starts · AI bot build · Simulation kicked off in parallel (two devs) · Login → Home/Dashboard. |
| W3 · Jul 7–13 | Regulatory build · Simulation build · Home/Dashboard → Policy detail + full-screen PDF. |
| W4 · Jul 14–20 | Regulatory review flow · Simulation build · Policy/Regulatory/Sim pages. |
| W5 · Jul 21–27 | Remaining UI · product tour · AI bot polish · simulation polish. |
| W6 · Jul 28–31 | Integrate, polish, sellable build (QA full regression). → Jul 31 milestone. |

Explicitly deferred out of July — policy drafting / PDF-edit (re-architects the publish+approval flow — define now, build later); full auto-scrape regulatory (v1.1); custom dashboards. Keeping these out is what makes the July date real.

Phase B — August onward: connectors + company brain

The connector itself is the easy part; the permission layer behind it is the gate. With the Sync team co-building — and now two dedicated devs plus a QA resource — the pace target moves to 9–10 connectors / month: a few hand-built (HRMS/proprietary) plus a heavily MCP-first long tail, with QA validating in parallel.

The gate — permission layer   [Sync team + QA]

Why it leads — every connector must mirror its source’s permissions into our RBAC (e.g. HRMS compensation visible only to CXO/HR). The permission layer (entities + entity-wise permissions) is defined once and reused as the bridge for every connector — so it must land by end-July or Phase B slips. The new dedicated QA owns its regression/verification, so “defined” means verified, not just declared.

Connector framework + ingestion   [Aug · one-time]

Platform tax — the first connector carries the framework + the snapshot→chunk→embed→VectorDB ingestion pipeline + permission mirroring. Largely one-time; subsequent connectors are far cheaper.

Connectors — 9–10 / month   [Aug–Nov]

Approach — HRMS first (mostly mapped via HyperSync — the proprietary edge; one connector, not 80), then go MCP-first hard for the long tail. The 9–10/month target is only realistic because most of the long tail is MCP/live — each is a fraction of a hand-built indexed connector (no ingestion pipeline, permissions inherited from the user’s own credentials) — so two devs + a dedicated QA validation rig clear 9–10/month. Hand-built indexed connectors remain the constraint at ~5–6.

| Month | Target | Candidate connectors | Cumulative |
| --- | --- | --- | --- |
| Aug | framework + 6 (ramp) | Keka, greytHR, Darwinbox (HRMS via HyperSync) · Jira · Notion · Slack | ~6 |
| Sep | 9–10 | Confluence · Google Drive · Gmail · Salesforce · HubSpot · Zoho · Zendesk · Freshdesk · BigQuery | ~16 |
| Oct | 9–10 | MS Teams · Outlook · SharePoint · NetSuite · ServiceNow + MCP long tail (per deal) | ~26 |
| Nov | 9–10 | MCP-first long tail (per deal) + warehouse/DB sources | ~35 |
| Dec+ | on demand | Long tail per deal (MCP-first) + hardening | 35+ |

Central brain (read-only)   [Sep–Nov]

What — as connectors accumulate, cross-source, permission-faithful Q&A across HRMS + policies + tickets + docs + comms. The industry-agnostic positioning starts here; private beta in September → GA in November.

Context / memory + hardening   [Oct–Nov]

What — an org graph / memory layer so it feels like a brain; instrumentation, eval harness, security hardening.

Agents — pull → governed push   [Q1–Q2 2027]

What — pull across the brain, then push (act/post) under RBAC with human-in-the-loop + audit (reusing the maker-checker rail). The earlier brain maturity lets a read-only compliance-agent prototype spike in December; governed push stays in 2027. Detailed agent design specified closer to the time.

Dependencies & risks

Permission layer is the gate — if it isn’t defined (and QA-verified) by end-July, the whole connector program slips. Treat it as a July exit-criterion.

The 9–10/month target depends on the long tail going MCP-first (hand-built indexed connectors sustain only ~5–6/month) and on both devs being ramped with the QA permission-regression suite live early — if the mix skews to hand-built or QA slips, the realistic floor is 5–6/month.

Regulatory needs the ecosystem map before build, or the multi-authority auto-scrape blocker bites again — hence manual-first.

Simulation scope must stay category-level (approval rate); custom per-policy variables will overrun the month.

Heavy connectors (Google Drive / Gmail / M365) carry vendor security review (Google CASA, M365 admin consent) — submit early so the 3–6 week calendar overlaps other work; they’re the months’ swing risk.

Connector rot — source APIs change; connectors and snapshots need maintenance. Ongoing cost, not one-time.

PRD discipline — each July feature is frozen from the prototype link before build; UI freezes via the prototype/design system with Devesh.

Open items

Naming — “Tara” vs the existing “Astron” chatbot; confirm with leadership.

Model packaging — Standard (bring-your-own-key, PLG, plug-and-play) vs Enterprise (on-prem, model configured via super-admin); pricing per user.

Policy drafting / PDF-edit — define the editor → save → re-approval flow now; schedule the build post-July.

Auto-scrape regulatory (v1.1) — scope after the manual flow ships and the regulator ecosystem is mapped.

See PolicyOS_Tara_Roadmap.xlsx for the visual Gantt (Gantt sheet), the per-workstream detail (Detail sheet), and the month-by-month connector plan (Connectors sheet).