## Gantt
PolicyOS · Tara — Product Roadmap (Gantt)
July = sellable build · August onward = connectors (9–10/mo — MCP-first long tail, 2 devs + 1 QA) + company brain · v2, 24 Jun 2026
PHASE | WORKSTREAM / FEATURE | JULY 2026 — Sellable build | [5 empty] | AUG–DEC 2026 — Connectors + company brain |  |  |  |  | 2027 — Agents
|  | W1 Jun 23–29 | W2 Jun 30–Jul 6 | W3 Jul 7–13 | W4 Jul 14–20 | W5 Jul 21–27 | W6 Jul 28–31 | Aug | Sep | Oct | Nov | Dec '26 | Q1 '27 | Q2 '27
★ Milestones | PRDs + AI demo (Jun 29) · Sellable build (Jul 31) · Permission-layer gate (end-Jul) · ~20 connectors by end-Sep, ~35 by end-Nov | ◆ 29 |  |  |  |  | ◆ 31 | ◆ gate | ◆ ~16 |  | ◆ ~35
July — sell | PRDs + regulator-ecosystem research + colour scheme
July — sell | Regulatory gaps (upload → impact → redline → approval) | PRD
July — sell | Test-based simulation (rule change → impact on test base) | PRD
July — sell | AI bot — unified Tara assistant (generic + per-policy, cited) | PRD
July — sell | UI · Login (PLG quick win)
July — sell | UI · Home / Dashboard (+ AI ask, eligibility)
July — sell | UI · Policy detail + full-screen PDF view
July — sell | UI · Regulatory / Simulation / PolyGPT + remaining
July — sell | Product guided tour (first N logins)
Gate | Permission layer (Sync team + QA — gates connectors) | [6 empty] | ◆
Aug+ — brain | Connector framework + ingestion pipeline
Aug+ — brain | Connectors · 9–10 / month (HRMS first, MCP-first long tail)
Aug+ — brain | Central brain — read-only (Sep beta → Nov GA) | [7 empty] | beta |  | GA
Aug+ — brain | Context / memory layer + hardening
2027 — act | Agents · pull → governed push (HITL + audit)
| Legend: |  | Build / active | PRD |  | Permission-layer gate |  | Connectors |  | Central brain |  |  | Agents (2027)

## Detail
Phase | Workstream / Feature | Window | PRD-gated | Owner / dependency | Sales impact | Scope notes
July — sell | Regulatory gaps | Jun 23 – Jul 31 | Yes (w/ Anmol) | Product + Eng (2 devs) | High | Manual flow first (upload → compare → AI redline → review → change request → approval). Auto-scrape of RBI/SEBI/MCA/MSME = v1.1. Map the regulator ecosystem before build.
July — sell | Test-based simulation | Jun 23 – Jul 31 | Yes | Product + Eng | High | Rule change → impact on a test user base; hold to category-level metrics (approval rate), client uploads test/dummy data. Keep separate from the half-baked test bed. With 2 devs it runs in parallel with Regulatory.
July — sell | AI bot (unified Tara assistant) | Jun 23 – Jul 27 | Yes | Eng (mostly in prototype) | High | Productionise the one ask surface: generic ask across accessible policies on Home + per-policy Q&A, with source chips + page citations. Retire the duplicate AI surfaces.
July — sell | UI revamp | Jun 23 – Jul 31 | Freeze via prototype link | Devesh (design) + Eng | High | Confirm colour scheme first. Order: Login → Home/Dashboard → Policy + full-screen PDF → Regulatory/Sim/PolyGPT → rest. Modern design system applied throughout.
July — sell | Product guided tour | Jul 21 – Jul 31 | No | Eng | Med | Drop-in overlay + tooltips for first N logins. Small effort.
Gate | Permission layer | → end-Jul (gate) | — | Sync team + dedicated QA | Enabler | HARD EXIT CRITERION for July even though not sellable. Entities + entity-wise permissions; reused as the bridge for every connector. The dedicated QA owns its regression so “defined” = verified. If it slips, Phase B slips.
Aug+ — brain | Connector framework + ingestion | Aug | Yes | Eng + Sync | Enabler | One-time platform tax: framework + snapshot→chunk→embed→VectorDB pipeline + permission mirroring. The first connector carries this cost.
Aug+ — brain | Connectors · 9–10 / month | Aug – Nov | Per connector | 2 devs + QA + Sync team | High (moat) | HRMS first (mostly mapped via HyperSync — one connector, not 80), then MCP-first for the long tail. 9–10/month is realistic only because the long tail is MCP/live (no ingestion, permissions inherited from the user’s own credentials) — hand-built indexed connectors sustain ~5–6. ~20 by end-Sep, ~35 by end-Nov.
Aug+ — brain | Central brain (read-only) | Sep – Nov | — | Eng | High | Cross-source, permission-faithful Q&A as connectors accumulate. Private beta Sep → GA Nov. Industry-agnostic positioning starts here.
Aug+ — brain | Context / memory + hardening | Oct – Nov | — | Eng + QA | Med | Org graph / memory so it feels like a brain; instrumentation, eval harness, security hardening.
2027 — act | Agents · pull → push | Q1 – Q2 '27 | Yes | Eng | High | Pull across the brain, then governed push (HITL + audit, reuse the maker-checker rail). Read-only compliance-agent prototype can spike in Dec; governed push stays 2027.

## Connectors (Aug+)
Month | Target | Candidate connectors | Method | Cumulative
Aug | framework + 6 (ramp) | Keka, greytHR, Darwinbox (HRMS via HyperSync) · Jira · Notion · Slack | HyperSync / API + MCP | ~6
Sep | 9–10 | Confluence · Google Drive · Gmail · Salesforce · HubSpot · Zoho · Zendesk · Freshdesk · BigQuery | API / MCP-first | ~16
Oct | 9–10 | MS Teams · Outlook · SharePoint · NetSuite · ServiceNow + MCP long tail (per deal) | API / MCP-first | ~26
Nov | 9–10 | MCP-first long tail (per deal) + warehouse/DB sources | MCP-first | ~35
Dec+ | as needed | Long tail per deal (MCP-first) + hardening | MCP-first | 35+
• Gated on the permission layer landing (and QA-verified) by end-July. The 9–10/month target is driven by MCP-first for the long tail (each MCP/live connector is a fraction of a hand-built one); hand-built indexed connectors sustain only ~5–6/month.
• HRMS via HyperSync = one connector, not 80 (the 80 are already normalized — that is the proprietary edge). Strategy: deep on the proprietary/hard (India HRMS, BFSI); MCP for the long tail — don’t hand-build a breadth war.
• Google Drive / Gmail / M365 carry vendor security review (Google CASA, M365 admin consent) — submit early so the 3–6 week calendar overlaps; they’re the months’ swing risk.